## Sheet1
Bug ID	Bug Description	Module	Steps to Reproduce	Expected Result	Actual Result	Severity	Priority	Assigned To	Status	Date Reported	Date Fixed	Comments
B001	Login Button Unresponsive	Login/Authentication	1. Open app | 2. Enter Valid username and password | 3. Tap on "Login" button	User should be logged in successfully	Button does not respond	High	High	Dev Team A	Open	13/11/2024		Known issue; impacts all users.
B002	Error in fund transfer amount	Fund Transfer	1. Login | 2. Go to Fund Transfern| 3. Enter amount exceeding balance	Show insufficient funds message	Allows input, then shows generic error	Critical	High	Dev Team B	In Progress	13/11/2024		Validation needs improvement.
B003	Logout redirects to home page	Logout	1. Login | 2. Click on "Logout"	User should be logged out to login screen	Redirects to app homepage	Medium	Medium	Dev Team A	Assigned	12/11/2024		Confusing for users, minor impact.
B004	App crash on adding payee	Add New Payee	1. Login | 2. Go to "Add New Payee" | 3. Enter valid payee details | 4. Submit	Payee should be added successfully	App crashes	High	High	Dev Team C	Open	10/11/2024		Issue identified, awaiting fix.
B005	Incorrect date format	Transaction History	1. Login | 2. Go to Transaction History | 3. View transaction date	Date format should be DD/MM/YYYY	Displayed as MM-DD-YYYY	Low	Low	Dev Team A	Fixed	05/11/2024		Fixed in latest update.
B006	Notification misalignment	Notifications	1. Login | 2. Go to "Notifications" | 3. Check notification alignment	Notifications should be aligned properly	Notifications misaligned	Low	Low	Dev Team B	Open	10/11/2024		UI issue, doesn’t impact function.
B007	Slow loading on transactions	Transaction History	1. Login | 2. Go to Transaction History | 3. Load transactions for past month	Transactions should load in < 3 sec	Takes 8-10 seconds to load	Medium	Medium	Dev Team C	In Progress	08/11/2024		Affects usability for some users.
B008	Double charge on payment	Payment	1. Login | 2. Make a payment | 3. Submit payment, screen freezes | 4. Payment charged twice	Payment should be charged once	User charged twice	Critical	Urgent	Dev Team D	Open	13/11/2024		Needs urgent fix; major impact.
B009	Missing confirmation message	Fund Transfer	1. Login | 2. Go to Fund Transfer | 3. Enter transfer details | 4. Submit	Show success confirmation message	No confirmation message shown	Medium	Medium	Dev Team B	Open	12/11/2024		Users confused if transfer succeeds.
B010	Password reset not working	Account Settings	1. Go to "Forgot Password" | 2. Enter registered email | 3. Submit	Password reset email should be sent	No email sent	High	High	Dev Team A	Open	09/11/2024		Affects user account recovery.