## Sheet1
Bug ID	Bug Description	Module	Steps to Reproduce	Expected Result	Actual Result	Severity	Priority	Assigned To	Status	Date Reported	Date Fixed	Comments
SM001	Profile picture not updating after upload	Profile Management	1. Go to profile | 2. Upload new picture | 3. Check updated profile	Profile picture should update and display correctly	Profile picture remains the same after upload	High	High	Dev Team A	Open	13/11/2024	-	Occurs intermittently; under investigation
SM002	Error loading user feed intermittently	User Feed	1. Login | 2. Go to 'Feed' page | 3. Refresh multiple times	User feed should load without errors	Intermittent loading errors on user feed	Critical	High	Dev Team B	In Progress	12/11/2024	-	Feeds load for some users only; backend check needed
SM003	Message notifications not clearing after read	Messaging	1. Open messaging tab | 2. Read notifications | 3. Check notification icon	Notifications should clear after reading	Notification icon remains active after reading	Medium	Medium	Dev Team C	Assigned	11/11/2024	-	Minor impact, affects user experience
SM004	User status not displaying as 'online' when active	User Status	1. Login | 2. Observe user status on profile | 3. User appears 'offline'	User status should display as 'online' when active	User appears 'offline' even when active	Low	Low	Dev Team D	Open	10/11/2024	-	Status display issue, low priority
SM005	Comment section crashes on specific posts	Comments	1. Go to a specific post | 2. Open comment section | 3. App crashes	Comment section should load without crashing	App crashes when opening comment section	High	High	Dev Team A	Open	09/11/2024	-	Crash occurs on posts with high comments
SM006	Live video freezing on low bandwidth	Live Video	1. Start a live video | 2. Reduce bandwidth | 3. Observe video playback	Live video should adjust quality and continue playing	Video freezes and fails to adjust quality	Medium	Medium	Dev Team E	In Progress	08/11/2024	-	Freezes often on low bandwidth connections
SM007	Followers count showing incorrect values	Followers Management	1. Open profile | 2. Check followers count | 3. Compare with actual followers	Followers count should reflect actual number	Followers count fluctuates or displays incorrectly	Low	Low	Dev Team B	Open	07/11/2024	-	Inconsistent follower count display
SM008	Password reset email not sent	Account Recovery	1. Go to login page | 2. Click 'Forgot Password' | 3. Check email inbox	Password reset email should be received	No email received for password reset	High	High	Dev Team C	Assigned	06/11/2024	-	Critical as users cannot reset passwords
SM009	New post images not loading in feed	Feed Images	1. Create a new post with images | 2. Check feed | 3. Images fail to load	Images should load correctly in the feed	Images fail to load in user feed	Critical	High	Dev Team D	In Progress	05/11/2024	-	Major issue, affecting media display
SM010	Unable to tag friends in comments	Tagging	1. Go to comments section | 2. Type '@' | 3. Friend tagging option missing	Friends should be taggable in comments	Unable to tag friends in comments section	Medium	Medium	Dev Team E	Assigned	04/11/2024	-	Tagging functionality missing in comments