## Sheet1
Bug ID	Bug Description	Module	Steps to Reproduce	Expected Result	Actual Result	Severity	Priority	Assigned To	Status	Date Reported	Date Fixed	Comments
OL001	Login button unresponsive on mobile view	Login/Authentication	1. Open mobile app | 2. Enter valid credentials | 3. Tap 'Login'	User should be logged in successfully	Button does not respond on mobile devices	High	High	Dev Team A	Open	2024-11-13		Issue reported by multiple users on mobile
OL002	Error loading course content for specific users	Course Content	1. Login | 2. Select course | 3. Attempt to load any lesson	Course content should load without errors	Error: 'Content unavailable' for some users	Critical	High	Dev Team B	In Progress	2024-11-12		Affects limited user group, being investigated
OL003	Quiz timer resets after page refresh	Quizzes	1. Start quiz | 2. Refresh page | 3. Observe timer	Quiz timer should continue without resetting	Timer resets to full time after refresh	Medium	Medium	Dev Team C	Assigned	2024-11-11		Impact on quiz functionality, needs prompt fix
OL004	Profile picture upload fails for certain image formats	User Profile	1. Login | 2. Go to 'Profile' | 3. Attempt to upload .png file	Image should upload and display in profile	Image upload fails, error: 'Invalid format'	High	High	Dev Team D	Open	2024-11-10		Occurs with .png and .gif formats, JPEG works fine
OL005	Notification panel displays duplicate messages	Notifications	1. Login | 2. Open notification panel	Notifications should display only once per message	Duplicate notifications appear in panel	Low	Low	Dev Team A	Fixed	2024-11-09	2024-11-10	Resolved in latest patch, duplicate check added
OL006	Video playback freezes midway in certain courses	Video Player	1. Login | 2. Start course video | 3. Play video halfway	Video should play smoothly until the end	Video freezes halfway through playback	Medium	Medium	Dev Team E	Open	08/11/2024	-	Specific to a few courses, ongoing investigation
OL007	Password reset link expired immediately after generation	Password Recovery	1. Go to login page | 2. Click 'Forgot Password' | 3. Use reset link	Password reset link should be valid for 24 hours	Link shows 'expired' error immediately	High	High	Dev Team B	Assigned	07/11/2024	-	Reset link time needs adjustment, critical for access
OL008	Course progress not saving for a few users	Progress Tracking	1. Login | 2. Complete a lesson | 3. Check course progress	User's progress should save automatically	Progress does not save after lesson completion	Critical	High	Dev Team C	In Progress	06/11/2024	-	Reported by several users, high priority
OL009	Discussion forum posts not visible after submission	Discussion Forum	1. Go to Discussion Forum | 2. Submit a post | 3. Refresh page	Forum post should be visible after submission	Submitted posts are not visible after refresh	Medium	Medium	Dev Team D	Open	05/11/2024	-	Posts disappear after refresh, backend check needed
OL010	Unable to download certificates from user profile	Certificates	1. Go to 'Certificates' in profile | 2. Click 'Download'	Certificate should download as a PDF	Download fails, 'file not found' error	High	High	Dev Team E	Assigned	04/11/2024	-	Issue with file generation, team investigating